PureSimple Web Framework Detailed Development Plan Phases • Features • UAT • Prompts • Git Workflow

# Development Overview

This plan decomposes the PureSimple web framework into 11 phases (P0–P10), each designed to be small enough for a solo developer to complete in 1–3 weeks. Each phase is independently testable and shippable. Phases are ordered by strict dependency: foundation first, then core framework, then application-layer features, then polish.

Every phase includes: feature implementation, unit tests, documentation updates, git workflow, PureBasic skill/pitfalls updates, and a ready-to-use AI prompt.

## Phase Roadmap

| Phase | Deliverable | Est. | Tier | Gin Features Mapped |
| --- | --- | --- | --- | --- |
| P0 | Project Foundation | 1 wk | Foundation | Project scaffolding |
| P1 | Core Router & Context | 2 wk | Foundation | Radix tree routing, path params, wildcards |
| P2 | Middleware Engine | 1 wk | Foundation | Middleware chain, Recovery, Logger |
| P3 | Request Binding & Validation | 2 wk | Core | Model binding, JSON/Form/Query, Validation |
| P4 | Response Rendering + PureJinja | 2 wk | Core | JSON/XML/HTML/String rendering, Templates |
| P5 | Route Groups & Error Handling | 1 wk | Core | RouterGroup, error collection, 404/405 |
| P6 | SQLite3 Integration | 2 wk | Application | DB integration examples from Gin docs |
| P7 | Sessions, Cookies & Auth | 2 wk | Application | BasicAuth, Cookie, Session middleware |
| P8 | Logging, Config & DX | 1 wk | Application | Custom log format, env config, run modes |
| P9 | Documentation & Tutorials | 2 wk | Polish | API reference, Quick Start, Developer Guide |
| P10 | Multi-DB Abstraction Layer | 3 wk | Extension | Multi-DB adapter (beyond Gin scope) |

# Standard Workflow (Every Phase)

The following 8-step workflow applies to every phase. This ensures consistency, traceability, and that documentation stays current.

| # | Step | Commands / Actions |
| --- | --- | --- |
| 1 | Create feature branch | git checkout -b feature/P{N}-{name} |
| 2 | Implement code | Write PureBasic source in src/; follow PureBasic skill + common-pitfalls.md |
| 3 | Write unit tests | Create test file in tests/; run test suite; all must pass |
| 4 | Update documentation | README.md (feature list), CHANGELOG.md (entry), CLAUDE.md (context) |
| 5 | Update skill & pitfalls | purebasic skill + resources/common-pitfalls.md if new patterns found |
| 6 | Commit & push | git add -A && git commit -m 'P{N}: description' && git push origin feature/P{N}-{name}' |
| 7 | Pull request & merge | Create PR; self-review checklist; merge to main; delete branch |
| 8 | Tag release | git tag v0.{N}.0 && git push --tags |
| 9 | Deploy to server | Run: ./scripts/deploy.sh (pulls, compiles, restarts service, health check) |
| 10 | Verify production | curl https://yourdomain.com/health — confirm 200 OK; check systemd logs |

## Integration Pattern: Three Repositories

PureSimple is a library that combines PureJinja and plugs into PureSimpleHTTPServer:

•  PureSimpleHTTPServer — provides the HTTP listener, TLS, compression, static serving. Your app’s main.pb includes PureSimpleHTTPServer and registers PureSimple’s dispatch callback as the request handler.

•  PureSimple — provides routing, middleware, context, binding, rendering. It receives raw request data from PureSimpleHTTPServer, processes it through the handler chain, and writes the response back.

•  PureJinja — provides template rendering. PureSimple’s HTML() renderer calls PureJinja’s CreateEnvironment/RenderString/FreeEnvironment API to process .html templates.

Recommended integration: git submodules or a shared include path. The final build compiles all three into a single binary.

# Deployment Pipeline

Every phase ends with a production deployment. The pipeline is fully automated via scripts created in P0.

Server: 129.212.236.80 • Ubuntu 24 • SSH root@port 22 (ed25519 key)

| # | deploy.sh Step | Details |
| --- | --- | --- |
| 1 | SSH connect | ssh -i ~/.ssh/id_ed25519 root@129.212.236.80 |
| 2 | Pull latest code | cd /opt/puresimple && git pull origin main |
| 3 | Compile binary | $PUREBASIC_HOME/compilers/pbcompiler src/main.pb -o app_new -e |
| 4 | Run tests on server | $PUREBASIC_HOME/compilers/pbcompiler tests/run_all.pb -e && ./run_all |
| 5 | Stop service | systemctl stop puresimple.service |
| 6 | Backup + swap binary | cp app app.bak && mv app_new app |
| 7 | Run DB migrations | ./app --migrate (if pending migrations exist) |
| 8 | Start service | systemctl start puresimple.service |
| 9 | Health check | curl -sf http://localhost:8080/health ¦¦ (rollback; exit 1) |
| 10 | Verify via Caddy | curl -sf https://yourdomain.com/health && echo DEPLOY OK |

## Server Configuration Files

| File | Purpose & Location |
| --- | --- |
| deploy/Caddyfile | Installed to /etc/caddy/Caddyfile. Config: yourdomain.com { reverse_proxy localhost:8080; encode gzip; log { output file /var/log/caddy/access.log } } |
| deploy/puresimple.service | Installed to /etc/systemd/system/. Unit: [Service] ExecStart=/opt/puresimple/app, Restart=on-failure, RestartSec=5, WorkingDirectory=/opt/puresimple, User=www-data, Environment=PURESIMPLE_MODE=release |
| deploy/setup-server.sh | One-time provisioning: mkdir /opt/puresimple, git clone all 3 repos, cp Caddyfile to /etc/caddy/, systemctl daemon-reload, systemctl enable puresimple caddy |
| scripts/deploy.sh | Developer runs locally. SSHs to server, executes the 10-step pipeline above. Exit code 0 = success, 1 = rolled back. |
| scripts/rollback.sh | Emergency rollback: SSH → stop → mv app.bak app → start → health check |

Phase 0: Project Foundation & CI Gin Reference: Project setup, go mod init, project structure

🎯 Goal

Set up the PureSimple git repository with proper structure, testing framework, CI configuration, and documentation templates. Establish the integration pattern between the three repositories.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | Repository structure | src/, tests/, docs/, examples/, resources/; .gitignore for PureBasic compiled files |
| 2 | Dependency integration | Define how PureSimple includes PureJinja (git submodule or copy) and plugs into PureSimpleHTTPServer (shared include path) |
| 3 | Test harness | Create a lightweight test runner in PureBasic; macro-based assertions: Assert(expr), AssertEqual(a,b), AssertString(a,b) |
| 4 | CLAUDE.md | PureBasic coding conventions, API version 2.0, project context for AI assistance |
| 5 | README.md | Project description, architecture diagram, build instructions, contributing guide |
| 6 | CHANGELOG.md | Initialized with v0.0.0 entry |
| 7 | common-pitfalls.md | PureBasic gotchas: string handling, memory management, thread safety, pointer arithmetic |
| 8 | scripts/deploy.sh | SSH to 129.212.236.80; git pull; pbcompiler; stop puresimple.service; swap binary (keep .bak); run migrations; start service; health check; print status |
| 9 | scripts/rollback.sh | SSH to server; stop service; swap app.bak back to app; start service; health check |
| 10 | deploy/puresimple.service | systemd unit: ExecStart=/opt/puresimple/app, Restart=on-failure, WorkingDirectory=/opt/puresimple, User=www-data |
| 11 | deploy/Caddyfile | yourdomain.com { reverse_proxy localhost:8080; encode gzip; log } |
| 12 | deploy/setup-server.sh | One-time: create /opt/puresimple, clone repos, install Caddyfile, enable systemd service |

🧪 Required Tests

•  Test harness self-test: Assert(#True), Assert(Not #False), AssertEqual(1+1, 2)

•  Build succeeds with empty framework stub

•  Include paths resolve PureJinja and PureSimpleHTTPServer headers

•  deploy.sh connects to server via SSH and runs health check

•  Caddyfile syntax validates with caddy validate

✅ UAT Acceptance Criteria

☑  Repository clones and builds on a clean machine

☑  Test harness runs and reports pass/fail with counts

☑  CLAUDE.md is accurate and up-to-date

☑  All 3 repos can be referenced from a single project

☑  ./scripts/deploy.sh deploys to server and curl /health returns 200

☑  Caddy reverse proxy serves the app on HTTPS

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P0-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P0: ...'), push, PR, merge, tag v0.0.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 1: Setting Up — Installing PureBasic, cloning the three repos, deployment scripts, building your first empty project

🤖 AI Prompt for This Phase

You are helping me set up Phase 0 of the PureSimple web framework for PureBasic. Create the initial repository structure for github.com/Jedt3D/PureSimple.git with: src/, tests/, docs/, examples/, resources/, scripts/, deploy/ directories. Create a PureBasic test harness with Assert(), AssertEqual(), AssertString() macros. Set up the integration pattern to include PureJinja (from github.com/Jedt3D/PureJinja) and plug into PureSimpleHTTPServer (from github.com/Jedt3D/PureSimpleHTTPServer). Write CLAUDE.md with PureBasic conventions and API v2.0 context. Write README.md with architecture overview. Initialize CHANGELOG.md. Create resources/common-pitfalls.md with known PureBasic gotchas. DEPLOYMENT: Create scripts/deploy.sh that SSHs to 129.212.236.80 (root, port 22, key ~/.ssh/id_ed25519), does: git pull, $PUREBASIC_HOME/compilers/pbcompiler to compile, stops puresimple.service, backs up old binary as app.bak, copies new binary, runs any pending migrations, starts service, curls /health endpoint to verify. Create scripts/rollback.sh that swaps app.bak back and restarts. Create deploy/puresimple.service (systemd unit with Restart=on-failure, WorkingDirectory=/opt/puresimple, User=www-data). Create deploy/Caddyfile (reverse_proxy localhost:8080 with encode gzip and access log). Create deploy/setup-server.sh for one-time server provisioning (create dirs, clone repos, install Caddyfile to /etc/caddy/, enable+start systemd service). Follow the purebasic skill in /Users/worajedt/.claude/skills/purebasic. All code must be PureBasic 6.x compatible with no external dependencies.

Phase 1: Core Router & Context Gin Reference: gin.Engine, httprouter radix tree, gin.Context, HTTP methods

🎯 Goal

Build the core routing engine (radix trie or sorted route table) and the Context struct that carries all per-request state through the handler chain.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | HandlerFunc type | Define Procedure HandlerFunc(*ctx.RequestContext) — the universal handler signature |
| 2 | Context struct | Fields: *Request, *Response, params map, query map, kv store, handlers[] array, handlerIndex, aborted flag |
| 3 | Context pool/reuse | Pre-allocate one Context per thread slot; reset fields at request start instead of allocating new |
| 4 | Router engine | One route table per HTTP method; insert and lookup operations; support for :param and *wildcard segments |
| 5 | HTTP method registration | GET(), POST(), PUT(), DELETE(), PATCH(), HEAD(), OPTIONS(), Any() |
| 6 | Route matching | Match incoming path against tree; extract named parameters; return handler chain |
| 7 | 404 / 405 handlers | NoRoute handler (404), NoMethod handler (405) — customizable |
| 8 | Basic app bootstrap | NewApp() → returns engine; app.Run(port) → starts PureSimpleHTTPServer with framework’s dispatch callback |

🧪 Required Tests

•  Register GET /hello and verify it matches

•  Register GET /users/:id and verify param extraction

•  Register POST /data and verify method isolation (GET /data returns 405)

•  Wildcard route /files/*path captures full suffix

•  404 returned for unregistered route

•  Context Reset() clears all fields

•  Context Set()/Get() key-value store works across handlers

✅ UAT Acceptance Criteria

☑  "Hello World" example: NewApp() + GET("/", handler) + Run(8080) serves a response

☑  Named params extracted correctly for /users/42

☑  405 returned when wrong method used

☑  Custom NoRoute handler overrides default 404

☑  All P1 tests pass; existing P0 tests still pass

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P1-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P1: ...'), push, PR, merge, tag v0.1.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 2: Hello World — Your first route, understanding the request lifecycle, serving a response

🤖 AI Prompt for This Phase

You are helping me build Phase 1 of PureSimple. Implement the core router and context. Create: (1) A HandlerFunc procedure type. (2) A RequestContext structure with: request method, path, headers, body, response status, response headers, response body buffer, params map, query map, key-value data store, handlers array (array of procedure pointers), handlerIndex integer, aborted boolean. (3) A router with one route table per HTTP method using a radix trie or sorted array. Support :param named segments and *wildcard. (4) Registration procedures: GET(), POST(), PUT(), DELETE(), PATCH(), HEAD(), OPTIONS(), Any(). (5) A match procedure that returns the handler chain + extracted params. (6) NoRoute/NoMethod default handlers (customizable). (7) NewApp() and Run(port) that wires into PureSimpleHTTPServer’s dispatch. Write comprehensive unit tests for all routing scenarios. Follow purebasic skill and common-pitfalls.md. Update README.md, CHANGELOG.md, CLAUDE.md.

Phase 2: Middleware Engine Gin Reference: gin.HandlerFunc chain, c.Next(), c.Abort(), Recovery(), Logger()

🎯 Goal

Implement the handler chain execution model that powers all middleware, including Next(), Abort(), and two essential built-in middleware: Logger and Recovery.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | Next() | Increments handlerIndex and calls the next handler in the chain; enables pre/post processing |
| 2 | Abort() | Sets handlerIndex to sentinel (array length); stops chain execution |
| 3 | AbortWithStatus(code) | Abort + set response status code (e.g., 401 Unauthorized) |
| 4 | Use() global middleware | app.Use(middleware) — prepend to all route handler chains |
| 5 | Handler chain concatenation | combineHandlers(): merges group middleware + route handlers into one flat array |
| 6 | Logger middleware | Logs: method, path, status, latency, timestamp; configurable format |
| 7 | Recovery middleware | Catches panics/crashes in handler chain; logs stack trace; returns 500 |
| 8 | Custom middleware pattern | Document how to write: check before → call Next() → check after |

🧪 Required Tests

•  Middleware executes in registration order

•  Next() resumes chain after middleware

•  Abort() stops remaining handlers from executing

•  AbortWithStatus() sets status AND stops chain

•  Logger middleware outputs correct format

•  Recovery middleware catches simulated crash, returns 500

•  Global Use() middleware runs on all routes

•  Multiple middleware compose correctly: Auth → Logger → Handler

✅ UAT Acceptance Criteria

☑  3-middleware chain executes in correct order (verified by output sequence)

☑  Abort in auth middleware prevents handler from running

☑  Recovery middleware catches crash and returns 500 without server dying

☑  Logger output shows method, path, status code, and timing

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P2-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P2: ...'), push, PR, merge, tag v0.2.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 3: Middleware — The pipeline pattern, writing your first middleware, logging and error recovery

🤖 AI Prompt for This Phase

You are helping me build Phase 2 of PureSimple. Implement the middleware engine. Create: (1) Next(*ctx) — increments handlerIndex, calls handlers[index](ctx). (2) Abort(*ctx) — sets handlerIndex to array length. (3) AbortWithStatus(*ctx, code) — abort + set status. (4) Use(middleware) on the app/engine to register global middleware. (5) combineHandlers() that merges group-level + route-level handlers into one array. (6) Built-in Logger middleware: logs method, path, status, latency. (7) Built-in Recovery middleware: catches errors, logs them, returns 500. (8) Document the custom middleware pattern (before → Next → after). Write unit tests for: execution order, Next() behavior, Abort() behavior, AbortWithStatus(), Logger output, Recovery from crash. Follow purebasic skill and common-pitfalls.md. Update all .md files.

Phase 3: Request Binding & Validation Gin Reference: c.Param(), c.Query(), c.ShouldBindJSON(), c.PostForm(), c.FormFile(), validation tags

🎯 Goal

Parse all incoming data formats: path params, query strings, JSON bodies, form data, and file uploads. Add basic validation helpers.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | Param(key) | Extract named path parameter from Context.params map |
| 2 | Query(key) / DefaultQuery(key, default) | Parse and return query string values |
| 3 | GetHeader(key) | Return request header value |
| 4 | BindJSON(*ctx, *map) | Parse JSON body into a Map structure; return error if malformed |
| 5 | PostForm(key) | Parse application/x-www-form-urlencoded body field |
| 6 | PostFormArray(key) | Return all values for a repeated form field |
| 7 | FormFile(key) | Parse multipart form file upload; return filename, size, content buffer |
| 8 | SaveUploadedFile() | Write uploaded file to disk path |
| 9 | Validation helpers | Required(value), IsEmail(value), MinLength(value, n), MaxLength(value, n), IsNumeric(value) |
| 10 | Content-Type detection | Auto-detect JSON vs Form vs Multipart from Content-Type header |

🧪 Required Tests

•  Param('id') returns '42' for /users/42

•  Query('page') returns '3' for ?page=3

•  DefaultQuery returns default when key missing

•  BindJSON parses valid JSON into map

•  BindJSON returns error on malformed JSON

•  PostForm extracts form field

•  FormFile extracts uploaded file name and content

•  Required() fails on empty string

•  IsEmail() validates correct/incorrect emails

•  Content-Type detection routes to correct parser

✅ UAT Acceptance Criteria

☑  All binding methods extract correct values

☑  Malformed JSON returns error without crash

☑  File upload saves to disk correctly

☑  Validation helpers reject bad input with clear error messages

☑  All P0-P3 tests pass together

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P3-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P3: ...'), push, PR, merge, tag v0.3.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 4: Handling Input — Forms, JSON, file uploads, and keeping your data clean with validation

🤖 AI Prompt for This Phase

You are helping me build Phase 3 of PureSimple. Implement request binding and validation. Create these Context methods: (1) Param(key) for path params. (2) Query(key), DefaultQuery(key, default) for query strings. (3) GetHeader(key). (4) BindJSON(*ctx, *map) to parse JSON request bodies. (5) PostForm(key), PostFormArray(key) for form-urlencoded data. (6) FormFile(key) for multipart file uploads. (7) SaveUploadedFile() to write file to disk. (8) Validation helpers: Required(), IsEmail(), MinLength(), MaxLength(), IsNumeric(). (9) Auto-detect Content-Type to choose parser. Use PureBasic’s built-in JSON library for parsing. Write tests for each method including edge cases (missing keys, malformed input, empty bodies). Follow purebasic skill and common-pitfalls.md. Update all .md files.

Phase 4: Response Rendering + PureJinja Gin Reference: c.JSON(), c.XML(), c.HTML(), c.String(), c.File(), c.Redirect(), SecureJSON, template rendering

🎯 Goal

Build all response output methods and integrate PureJinja for HTML template rendering.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | JSON(status, data) | Serialize Map/List to JSON string; set Content-Type: application/json |
| 2 | IndentedJSON(status, data) | Pretty-printed JSON for debugging |
| 3 | SecureJSON(status, data) | Prefix with )]}' to prevent JSON hijacking |
| 4 | String(status, format, ...) | Plain text response with Content-Type: text/plain |
| 5 | HTML(status, template, data) | Render PureJinja template with data map; Content-Type: text/html |
| 6 | File(filepath) | Serve static file with correct Content-Type and caching headers |
| 7 | FileAttachment(filepath, name) | Serve file as download with Content-Disposition header |
| 8 | Redirect(status, url) | 301/302 redirect response |
| 9 | Status(code) | Set status code without body |
| 10 | SetHeader(key, value) | Set response header |
| 11 | SetCookie(name, value, ...) | Set response cookie with path, domain, maxAge, secure, httpOnly |
| 12 | Template loader | Load PureJinja templates from directory; cache compiled templates |
| 13 | Template functions | Register custom template functions accessible from all templates |
| 14 | Error page templates | Default 404.html and 500.html; customizable |

🧪 Required Tests

•  JSON() produces valid JSON with correct Content-Type

•  IndentedJSON() output is human-readable

•  SecureJSON() has anti-hijack prefix

•  String() outputs plain text

•  HTML() renders PureJinja template with variable substitution

•  HTML() supports template inheritance (extends/block)

•  File() serves file with correct MIME type

•  Redirect() sets Location header and status

•  SetCookie() produces valid Set-Cookie header

•  Template cache avoids re-parsing on second render

✅ UAT Acceptance Criteria

☑  Full request cycle works: route → handler → JSON response readable by curl

☑  PureJinja template renders correctly with passed data

☑  Template inheritance works (base.html → page.html)

☑  Static file serving returns correct content and headers

☑  All P0-P4 tests pass together

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P4-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P4: ...'), push, PR, merge, tag v0.4.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 5: Rendering Responses — JSON APIs, HTML templates, file downloads, and the PureJinja connection

🤖 AI Prompt for This Phase

You are helping me build Phase 4 of PureSimple. Implement response rendering and PureJinja integration. Create: (1) JSON(), IndentedJSON(), SecureJSON() for JSON output. (2) String() for plain text. (3) HTML(status, templateName, dataMap) that calls PureJinja’s RenderString/RenderFile with the data. (4) File() and FileAttachment() for file serving. (5) Redirect(). (6) Status(), SetHeader(), SetCookie(). (7) A template loader that loads .html files from a templates/ directory and caches compiled PureJinja environments. (8) Default 404.html and 500.html error page templates. Integration: PureJinja is included via its CreateEnvironment/RenderString/FreeEnvironment API. Write tests for every renderer. Follow purebasic skill. Update all .md files.

Phase 5: Route Groups & Error Handling Gin Reference: gin.RouterGroup, r.Group(), Gin error collection, c.Error(), c.Errors

🎯 Goal

Add route grouping with shared prefixes/middleware, and structured error collection on the Context.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | Group(prefix) | Create a sub-router with shared path prefix; inherits parent middleware |
| 2 | Nested groups | Groups can nest: app.Group('/api').Group('/v1').GET('/users', handler) |
| 3 | Group-level Use() | Middleware applied only to routes in this group |
| 4 | Error collection | ctx.Error(err) appends to an error list; ctx.Errors returns all collected errors |
| 5 | Error types | Typed errors: BindError, ValidationError, InternalError with code + message |
| 6 | Error middleware | ErrorHandler middleware that formats collected errors into JSON/HTML response |
| 7 | Custom 404 per group | Different NoRoute handler for /api/* (JSON 404) vs / (HTML 404) |
| 8 | Static file group | app.Static('/assets', './public') — shortcut for file-serving route group |

🧪 Required Tests

•  Group('/api') prefixes all child routes

•  Nested groups: /api/v1/users resolves correctly

•  Group middleware runs only for group routes

•  Parent middleware runs before group middleware

•  ctx.Error() collects multiple errors

•  ctx.Errors returns all in order

•  ErrorHandler middleware formats errors as JSON

•  Static('/assets', dir) serves files from directory

•  Different 404 handlers per group work correctly

✅ UAT Acceptance Criteria

☑  API group returns JSON errors; web group returns HTML errors

☑  Route groups compose: /api/v1/users, /api/v2/users from nested groups

☑  Static file serving works via group shortcut

☑  Error collection visible in middleware for logging/reporting

☑  All P0-P5 tests pass together

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P5-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P5: ...'), push, PR, merge, tag v0.5.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 6: Organizing Routes — Route groups, API versioning, error handling patterns

🤖 AI Prompt for This Phase

You are helping me build Phase 5 of PureSimple. Implement route groups and error handling. Create: (1) Group(prefix) that returns a new RouterGroup with shared path prefix. (2) Nested groups support. (3) Group-level Use() for group-scoped middleware. (4) ctx.Error(err) to append errors to Context.errors list. (5) Error types: BindError, ValidationError, InternalError with code and message. (6) ErrorHandler middleware that checks ctx.Errors and formats response. (7) Custom NoRoute per group (JSON 404 for /api/*, HTML 404 for /). (8) Static(prefix, directory) shortcut for static file serving groups. Write unit tests. Follow purebasic skill. Update all .md files.

Phase 6: SQLite3 Integration Gin Reference: Gin DB integration examples, model binding with database

🎯 Goal

Integrate SQLite3 with connection management, query helpers, and a simple migration runner. Design the interface to support future PostgreSQL/MySQL adapters.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | DB interface | Abstract DBAdapter interface: Open(), Close(), Query(), QueryRow(), Exec(), Begin(), Commit(), Rollback() |
| 2 | SQLite3 adapter | Concrete implementation using PureBasic’s built-in SQLite3 library |
| 3 | Connection middleware | Middleware that sets *db on Context so handlers can access ctx.DB() |
| 4 | Query helpers | QueryMap() returns List of Maps; QueryValue() returns single value |
| 5 | Parameterized queries | Prevent SQL injection: db.Query('SELECT * FROM users WHERE id = ?', id) |
| 6 | Transaction support | db.Begin() → db.Exec() → db.Commit() / db.Rollback() |
| 7 | Migration runner | Read .sql files from migrations/ directory; track applied versions in _migrations table |
| 8 | Seed data | db.Seed(filepath) — run SQL seed file for development data |

🧪 Required Tests

•  Open and close SQLite3 database

•  Insert and select a row

•  Parameterized query prevents injection (test with single-quote input)

•  Transaction commit persists data

•  Transaction rollback discards data

•  Migration runner applies files in order

•  Migration runner skips already-applied migrations

•  QueryMap returns correct map structure

•  Connection middleware makes db available on context

✅ UAT Acceptance Criteria

☑  CRUD operations work through the framework’s DB helpers

☑  Migrations run on fresh database correctly

☑  Transaction rollback actually discards changes

☑  SQL injection attempt via parameter is safely escaped

☑  All P0-P6 tests pass together

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P6-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P6: ...'), push, PR, merge, tag v0.6.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 7: The Database — SQLite3 integration, migrations, CRUD operations, protecting against injection

🤖 AI Prompt for This Phase

You are helping me build Phase 6 of PureSimple. Implement SQLite3 integration with an abstraction layer. Create: (1) A DBAdapter interface with Open(), Close(), Query(), QueryRow(), Exec(), Begin(), Commit(), Rollback(). (2) SQLite3Adapter implementing that interface using PureBasic’s built-in SQLite3 library. (3) Connection middleware that attaches db to context. (4) Query helpers: QueryMap() (returns List of Maps), QueryValue() (single value). (5) Parameterized queries to prevent SQL injection. (6) Transaction support with Begin/Commit/Rollback. (7) Migration runner that reads .sql files from migrations/ and tracks versions in _migrations table. (8) Seed() function. Write tests including SQL injection prevention test. Follow purebasic skill. Update all .md files.

Phase 7: Sessions, Cookies & Auth Gin Reference: gin-contrib/sessions, BasicAuth middleware, cookie handling

🎯 Goal

Implement server-side sessions backed by cookies, BasicAuth middleware, and CSRF protection.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | Cookie helpers | ctx.Cookie(name), ctx.SetCookie(name, value, maxAge, path, domain, secure, httpOnly) |
| 2 | Session middleware | Server-side sessions stored in SQLite3; session ID in cookie; configurable expiry |
| 3 | Session API | ctx.Session.Get(key), Set(key, value), Delete(key), Clear(), Save() |
| 4 | Flash messages | ctx.Session.AddFlash(msg, category); ctx.Session.Flashes(category) |
| 5 | BasicAuth middleware | Validates Authorization header against user/password map; returns 401 on failure |
| 6 | CSRF middleware | Generate token; validate on POST/PUT/DELETE; inject into templates as {{ csrf_token }} |
| 7 | Auth helper | ctx.MustGet('user') pattern for authenticated user access |
| 8 | Secure cookie signing | HMAC-sign cookie values to prevent tampering |

🧪 Required Tests

•  Set and read cookie

•  Session stores and retrieves values

•  Session persists across simulated requests (same session ID)

•  Session expires after configured time

•  Flash message readable once then deleted

•  BasicAuth accepts valid credentials

•  BasicAuth rejects invalid credentials with 401

•  CSRF token validates on POST

•  CSRF rejects request with missing/wrong token

•  Signed cookie detects tampering

✅ UAT Acceptance Criteria

☑  Login flow works: form → BasicAuth → session create → redirect

☑  Session data persists across requests

☑  CSRF protection prevents cross-site form submission

☑  Signed cookies reject tampered values

☑  All P0-P7 tests pass together

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P7-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P7: ...'), push, PR, merge, tag v0.7.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 8: Users & Sessions — Authentication, sessions, CSRF protection, keeping users logged in

🤖 AI Prompt for This Phase

You are helping me build Phase 7 of PureSimple. Implement sessions, cookies, and authentication. Create: (1) Cookie helpers on Context: Cookie(name), SetCookie(). (2) Session middleware backed by SQLite3: stores session data server-side, session ID in cookie. (3) Session API: Get(), Set(), Delete(), Clear(), Save(). (4) Flash messages: AddFlash(), Flashes(). (5) BasicAuth middleware: validates Authorization header against accounts map; returns 401 on failure. (6) CSRF middleware: generates token on GET, validates on POST/PUT/DELETE, available in templates as {{ csrf_token }}. (7) Secure cookie signing with HMAC. Write tests for all scenarios. Follow purebasic skill. Update all .md files.

Phase 8: Logging, Config & Developer Experience Gin Reference: gin.SetMode(), gin.DebugPrintRouteFunc, custom log format, run modes

🎯 Goal

Add structured logging, environment configuration, run modes, and developer convenience features.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | Run modes | Debug, Release, Test modes; Debug shows detailed errors + route table on startup |
| 2 | SetMode(mode) | Switch between debug/release/test; affects error detail and logging verbosity |
| 3 | Structured logger | JSON-formatted log output option; log levels: DEBUG, INFO, WARN, ERROR |
| 4 | Log to file | Logger middleware option to write to file instead of stdout |
| 5 | Environment config | LoadEnv('.env') reads key=value file; os.Getenv() equivalent; override with actual env vars |
| 6 | Route table printer | On startup in debug mode, print all registered routes with methods and paths |
| 7 | Scaffold generator | NewProject(name) creates directory structure with example main.pb, templates/, static/ |
| 8 | Graceful hints | Document how to handle SIGINT/SIGTERM for clean shutdown of PureSimpleHTTPServer |

🧪 Required Tests

•  Debug mode shows verbose errors

•  Release mode hides internal error details

•  Logger writes valid JSON when JSON mode enabled

•  Log file output creates and appends to file

•  LoadEnv() parses .env file correctly

•  Environment variable overrides .env value

•  Route table prints all registered routes

•  Scaffold creates expected directory structure

✅ UAT Acceptance Criteria

☑  Debug mode startup shows route table + verbose errors

☑  Release mode shows user-friendly error pages

☑  .env loading works for database path and port config

☑  Scaffold generates a runnable Hello World project

☑  All P0-P8 tests pass together

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P8-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P8: ...'), push, PR, merge, tag v0.8.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 9: Going Professional — Logging, configuration, project structure, and debug vs production modes

🤖 AI Prompt for This Phase

You are helping me build Phase 8 of PureSimple. Implement logging, config, and developer experience. Create: (1) Run modes: Debug/Release/Test via SetMode(). Debug shows detailed errors and route table; Release hides internals. (2) Structured logger with levels (DEBUG, INFO, WARN, ERROR) and optional JSON output format. (3) Log-to-file option for the Logger middleware. (4) LoadEnv('.env') to read key=value config files. (5) Route table printer on debug startup. (6) NewProject(name) scaffold generator that creates directory structure with example files. (7) Document graceful shutdown pattern. Write tests. Follow purebasic skill. Update all .md files.

Phase 9: Documentation & Tutorials Gin Reference: Gin official docs structure: Introduction, Quickstart, Examples, API

🎯 Goal

Write comprehensive documentation: API reference, quick start tutorial, developer guide, and outline the companion book.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | API Reference | Document every public procedure: signature, params, return value, example; organized by module |
| 2 | Quick Start Tutorial | Step-by-step: install → hello world → add route → add template → add database → deploy |
| 3 | Developer Guide | Architecture deep-dive: how the router works, middleware internals, extending the framework |
| 4 | Integration Guide | How to set up all 3 repos together; Makefile/build script; deployment with Caddy |
| 5 | Example applications | Todo app (CRUD + sessions); API-only microservice (JSON + auth); Blog (templates + DB) |
| 6 | Book outline | Chapter-by-chapter plan for 'Agile Web Development with PureSimple' following P0-P10 progression |
| 7 | Contributing guide | How to contribute to PureSimple; code style; PR process; test requirements |
| 8 | FAQ / Troubleshooting | Common issues: build errors, path issues, template not found, DB locked |

🧪 Required Tests

•  API reference covers all public procedures

•  Quick start tutorial runs successfully on clean checkout

•  All example apps build and run

•  Links between docs are valid

•  Code samples in docs compile

✅ UAT Acceptance Criteria

☑  A new developer can follow Quick Start and have a running app in 15 minutes

☑  API reference is complete (no undocumented public procedures)

☑  Example todo app demonstrates full CRUD lifecycle

☑  Book outline covers all phases as chapters

☑  All P0-P9 tests pass together

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P9-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P9: ...'), push, PR, merge, tag v0.9.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 10-12: Building a Real Application — The todo app, deploying to production, what’s next

🤖 AI Prompt for This Phase

You are helping me build Phase 9 of PureSimple. Write comprehensive documentation. Create: (1) docs/api-reference.md — every public procedure with signature, params, return, example. (2) docs/quick-start.md — step-by-step from install to deployed app. (3) docs/developer-guide.md — architecture, router internals, extending the framework. (4) docs/integration-guide.md — setting up all 3 repos, build script, Caddy deployment. (5) examples/todo-app/ — full CRUD todo application with sessions and templates. (6) examples/api-service/ — JSON-only microservice with auth. (7) docs/book-outline.md — chapter plan for the companion book. (8) CONTRIBUTING.md. (9) docs/faq.md. Review all existing docs for accuracy. Follow purebasic skill. Update all .md files.

Phase 10: Multi-DB Abstraction Layer Gin Reference: Beyond Gin: database abstraction, connection pooling, adapter pattern

🎯 Goal

Extend the DBAdapter interface with PostgreSQL and MySQL adapters. Implement connection pooling and adapter auto-detection from config.

🔧 Features to Implement

| # | Feature | Details |
| --- | --- | --- |
| 1 | PostgreSQL adapter | Implement DBAdapter using libpq C bindings via PureBasic ImportC |
| 2 | MySQL adapter | Implement DBAdapter using libmysqlclient C bindings via PureBasic ImportC |
| 3 | Connection pooling | Pool of N connections; checkout/checkin pattern; configurable pool size |
| 4 | Config-driven adapter | LoadEnv DB_DRIVER=sqlite3¦postgres¦mysql auto-selects adapter |
| 5 | Query dialect handling | Abstract placeholder style: ? for SQLite3/MySQL, $1 for PostgreSQL |
| 6 | Migration compatibility | Migration runner works across all three databases |
| 7 | Connection health check | Ping() method; auto-reconnect on connection loss |
| 8 | Documentation update | Update all docs/examples to show multi-DB configuration |

🧪 Required Tests

•  PostgreSQL adapter connects, queries, and disconnects

•  MySQL adapter connects, queries, and disconnects

•  Same application code works with all 3 adapters (swap config only)

•  Connection pool limits concurrent connections

•  Pool recycles connections after checkin

•  Placeholder translation works (? → $1 for Postgres)

•  Migration runner applies same migrations to all DBs

•  Health check detects dead connection and reconnects

✅ UAT Acceptance Criteria

☑  Switch DB_DRIVER in .env and app works with no code changes

☑  Connection pool handles concurrent requests without errors

☑  Migrations run identically on SQLite3, PostgreSQL, and MySQL

☑  All P0-P10 tests pass together

☑  Companion book updated with multi-DB chapter

📋 Phase Workflow (Every Phase)

1. git checkout -b feature/P10-{name}

2. Implement code following PureBasic skill + common-pitfalls.md

3. Write tests; run full suite; fix until 100% pass

4. Update README.md, CHANGELOG.md, CLAUDE.md

5. Update purebasic skill + resources/common-pitfalls.md

6. git add, commit ('P10: ...'), push, PR, merge, tag v0.10.0

7. ./scripts/deploy.sh → verify https://yourdomain.com/health returns 200

📖 Book Chapter Mapping

Chapter 13: Scaling Up — PostgreSQL, MySQL, connection pooling, and choosing the right database

🤖 AI Prompt for This Phase

You are helping me build Phase 10 of PureSimple. Implement multi-database support. Create: (1) PostgreSQLAdapter implementing DBAdapter via libpq C bindings (PureBasic ImportC). (2) MySQLAdapter implementing DBAdapter via libmysqlclient C bindings. (3) Connection pool: configurable size, checkout/checkin, max lifetime. (4) Config-driven adapter selection: DB_DRIVER env var. (5) Query placeholder translation (? → $N for PostgreSQL). (6) Ensure migration runner works across all databases. (7) Ping() health check with auto-reconnect. (8) Update all documentation for multi-DB. Write tests for each adapter. Follow purebasic skill. Update all .md files.